## Breakdown
SEO Retainer Breakdown
| Consulting Hours | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Technical Hours | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| Content Hours | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
| Link Hours | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6

## 1. Client Detail
SEO Retainer Agreement
Client Name | Helen Kaminski
Industry | Accessories
Monthly Retainer (excl tech fees) | 4906 | (excl. tech — see separate line)
Project Start Date | 2026-01-01
CMS | Shopify
Primary Contact | to be provided | Please enter contact name
Account Manager | SEO to add
Domain | double click to enter
Notes | TBC: confirm retainer split

## 2. Consulting
Consulting Tasks
Task | Focus | Occurrence | Hours
Monthly Strategy Review | Strategy | Monthly | 4
Keyword Research & Mapping | Strategy | 6 Months | 8
Competitor Analysis | Strategy | 6 Months | 6
GA4 & GSC Reporting | Analytics | Monthly | 3
Content Gap Analysis | Strategy | 6 Months | 8
Backlink Profile Review | Off-Page | 6 Months | 4

## 3. Technical
Technical SEO Tasks
| Task | Focus | Occurrence | Hours
Month 1 | Core Web Vitals Audit | Technical | Monthly | 6
Month 1 | Crawl Error Remediation | Technical | Monthly | 4
Month 2 | Schema Markup Implementation | Technical | 6 Months | 8
Month 2 | Site Speed Optimisation | Technical | Monthly | 4
Month 3 | Internal Linking Audit | Technical | 6 Months | 10
Month 3 | Redirect Chain Cleanup | Technical | 6 Months | 6

## 4. Content
Content Production Plan
Month | Month Name | URL | Title | Focus | Priority | Content Type | Word Count | SEO Hours | Brief / Notes
1 | Jan | https://helenkaminski.com/blog/silk-scarves-guide | Silk Scarves Style Guide | Content | High | New Page | 300 | 2
1 | Jan | https://helenkaminski.com/blog/accessories-trends | Accessories Trends 2026 | Content | High | New Page | 300 | 2
2 | Feb | https://helenkaminski.com/blog/straw-bags-summer | Straw Bags Summer Edit | Content | Medium | New Page | 300 | 2
2 | Feb | https://helenkaminski.com/blog/raffia-hat-guide | Raffia Hat Ultimate Guide | Content | Medium | New Page | 300 | 2
3 | Mar | https://helenkaminski.com/blog/gift-guide-women | Gift Guide for Women | Content | High | New Page | 300 | 2
1 | Jan | https://helenkaminski.com/hats | Hats Category Page | Content | High | Optimisation | 200 | 1
2 | Feb | https://helenkaminski.com/scarves | Scarves Category Page | Content | Medium | Optimisation | 200 | 1
3 | Mar | https://helenkaminski.com/bags | Bags Category Page | Content | Medium | Optimisation | 200 | 1
1 | Jan | https://helenkaminski.com/faq/hat-sizing | Hat Sizing FAQ | Content | Low | FAQ | 150 | 1
2 | Feb | https://helenkaminski.com/faq/care-instructions | Care Instructions FAQ | Content | Low | FAQ | 150 | 1
1 | Jan | https://helenkaminski.com.au/blog/silk-scarves-guide | Silk Scarves Style Guide AU | Content | High | New Page | 150 | 1.5 | localisation
1 | Jan | https://helenkaminski.com.au/blog/accessories-trends | Accessories Trends 2026 AU | Content | High | New Page | 150 | 1.5 | localisation
2 | Feb | https://helenkaminski.com.au/blog/straw-bags-summer | Straw Bags Summer Edit AU | Content | Medium | New Page | 150 | 1.5 | localisation
3 | Mar | https://helenkaminski.com.au/hats | Hats AU Category Page | Content | High | Optimisation | 100 | 1 | localisation
3 | Mar | https://helenkaminski.com.au/scarves | Scarves AU Category Page | Content | Medium | Optimisation | 100 | 1 | localisation
2 | Feb | https://helenkaminski.co.nz/blog/straw-bags-summer | Straw Bags Summer Edit NZ | Content | Low | New Page | 150 | 1.5 | localisation
3 | Mar | https://helenkaminski.co.nz/hats | Hats NZ Category Page | Content | Low | Optimisation | 100 | 1 | localisation

## 5. Links
Link Building Tasks
Task | Focus | Occurrence | Hours
Digital PR Outreach | Off-Page | Monthly | 4
Guest Post Sourcing | Off-Page | Monthly | 2
Link Reclamation | Off-Page | 6 Months | 3
Competitor Backlink Analysis | Strategy | 6 Months | 4